## Slide 1
CSE 0613-2209 · Web Programming
Module 3: Methodology Deep Dive & Relationship Analysis
Week 5, Day 1 — Development Methodologies
Waterfall, Agile, RAD, and Spiral — compared side by side, with a burndown chart, a decision matrix, and a real $170M cautionary tale.
Department of Computer Science and Engineering
Notes: Welcome to Module 3. Bridge from Module 2: we've analysed requirements, design, security, and performance for an existing system. Now we shift to the process used to build a system in the first place — starting with four foundational models.

## Slide 2
WEEK 5 · DAY 1
This Session at a Glance
What a development methodology is, and why the choice matters
Four models in depth — Waterfall, Agile, RAD, and Spiral — each with a diagram
A structured comparison matrix across all four
Reading a sprint burndown chart
A decision matrix for picking the right model, applied to a real scenario
Why This Matters
The methodology you choose determines how requirements changes, risk, and feedback are handled — get it wrong, and even good requirements (Week 3) can produce a failed project, as today's case study shows.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
2
Notes: Preview the five topics. This session sets up Day 2 (Agile Rituals & Spiral Risk), which goes deeper into two of today's four models.

## Slide 3
5.1 FOUNDATIONS
What Is a Development Methodology?
Definition
A structured approach to organising the activities of software development — when requirements are gathered, how design and coding proceed, and when testing and feedback happen.
The Core Question Each Answers
How much do we plan up front, versus how much do we discover and adjust as we go? Every methodology sits somewhere on this spectrum.
Why It's Not One-Size-Fits-All
A methodology that fits a well-understood, stable-requirements project can fail badly on a project with evolving, unclear requirements — and vice versa.
Today's Four Models
Waterfall (fully sequential), Agile (iterative, adaptive), RAD (rapid prototyping), and Spiral (risk-driven, cyclical) — spanning the full planning-vs-adapting spectrum.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
3
Notes: Frame the whole session around one spectrum: up-front planning vs. adaptive discovery. Waterfall sits at one extreme, Agile near the other, with RAD and Spiral occupying different middle positions for different reasons.

## Slide 4
FIGURE 5.1 · WATERFALL
The Waterfall Model
Strictly sequential phases — each one completes fully before the next begins.
Requirements
Design
Implementation
Testing
Deployment
Maintenance
Trade-off
Predictable and easy to manage on paper, but expensive to reverse — discovering a wrong requirement in Testing means walking back through Design and Implementation.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
4
Notes: The 'staircase' visual is intentional — each phase is complete and signed off before the next starts, which is exactly what makes late-discovered problems so expensive to fix under this model.

## Slide 5
FIGURE 5.2 · AGILE
The Agile Model
Short, repeating cycles that each deliver a working increment and gather feedback.
Plan
Design
Build
Test
Review
Sprint
(1-4 wks)
Trade-off
Adapts quickly to changing requirements and surfaces problems early, but requires continuous stakeholder engagement and can lose sight of long-term architecture.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
5
Notes: Unlike Waterfall's straight line, this is a closed loop repeated every sprint — the same five stages happen again and again, each time producing a working increment rather than a document.

## Slide 6
FIGURE 5.3 · RAD
The RAD Model (Rapid Application Development)
Fast, iterative prototyping cycles built directly with user feedback, prioritising speed to a usable prototype.
Requirements Planning
Business and technical scope agreed quickly with users present
User Design
Users work directly with prototypes, refining screens live
Rapid Construction
Prototype is built out into working software, often with reusable components
Cutover
System is tested and transitioned into production use
Repeat User Design ⟷ Construction until the prototype satisfies users
Trade-off
Extremely fast for well-scoped applications with active user involvement, but risks skipping rigorous architecture and non-functional analysis in the rush toward a working prototype.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
6
Notes: RAD is distinct from Agile in emphasis: RAD prioritises speed to a working prototype (often with heavy code reuse/component libraries), while Agile prioritises adapting to changing requirements over many repeated cycles.

## Slide 7
FIGURE 5.4 · SPIRAL
The Spiral Model
Each loop repeats four activities, with an explicit risk-analysis step before committing further investment.
1. Objectives
Determine goals, alternatives, constraints for this loop
2. Risk Analysis
Evaluate alternatives; identify and resolve the biggest risks
3. Engineering
Develop and verify the next-level product increment
4. Planning
Review progress; plan the next loop around the spiral
Start
Trade-off
The explicit risk-analysis step suits large, high-risk, high-cost projects well, but adds overhead that's hard to justify for smaller, lower-risk work.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
7
Notes: The spiral literally gets larger each loop — early loops are cheap, small-scope explorations of risk; later loops involve progressively larger investment as risk is retired. This is the model covered in more depth on Day 2, alongside the Cost-of-Change curve.

## Slide 8
5.1 COMPARISON MATRIX
Four Models — Structured Comparison
Dimension | Waterfall | Agile | RAD | Spiral
Planning style | Fully up-front | Just-in-time, per sprint | Light, evolves with prototype | Explicit, revisited each loop
Handles changing requirements | Poorly | Very well | Well, if scope is contained | Well, via risk reassessment
Risk management | Implicit / late | Ongoing via short cycles | Limited | Explicit, formal step
Best fit | Stable, well-understood scope | Evolving, customer-driven scope | Small-to-mid apps, active users | Large, high-risk, high-cost projects
Documentation | Heavy, upfront | Light, just enough | Light, prototype-driven | Moderate to heavy per loop
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
8
Notes: Use this table as the anchor recap for all four models — every row should let students recall the specific diagram from earlier in the session.

## Slide 9
FIGURE 5.5
Reading a Sprint Burndown Chart
Tracks remaining work (story points) against time — the gap between ideal and actual reveals whether a sprint is on track.
Chart: Story points remaining
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Ideal burndown | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
Actual burndown | 50 | 48 | 46 | 44 | 40 | 38 | 30 | 22 | 14 | 6 | 0
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
9
Notes: Point out the shape: the team fell behind the ideal line through Day 6 (a classic mid-sprint lag), then burned down faster in the last three days to catch up — a pattern worth discussing at retro, since a late rush often means quality was rushed too.

## Slide 10
5.1 BURNDOWN PATTERNS
What Different Burndown Shapes Mean
Pattern | What It Suggests | Likely Action
Tracks the ideal line closely | Estimation and pace are well-calibrated | Keep the current sprint planning approach
Flat line for several days, then a steep drop | Work was batched and marked done late, not steadily | Break stories smaller; update status daily, not at the end
Line trends upward mid-sprint | New scope was added after the sprint started | Protect sprint scope; queue new requests for next sprint
Never reaches zero | Team consistently over-commits relative to real capacity | Recalibrate velocity using recent sprints, not optimism
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
10
Notes: This table turns the previous chart into a diagnostic tool — have students classify the previous slide's actual line against these four patterns (it matches the second pattern: work marked done late in the sprint).

## Slide 11
5.1 DECISION MATRIX
A Decision Matrix for Choosing a Model
If your project has… | Waterfall | Agile | RAD | Spiral
Stable, fully understood requirements | Best fit | Overkill | OK | Overkill
Requirements likely to change | Poor fit | Best fit | OK | OK
Small scope, active user involvement | OK | Good fit | Best fit | Overkill
Large scope, high cost, high risk | Risky | OK at scale | Poor fit | Best fit
Hard compliance / audit requirements | Good fit | OK with discipline | Poor fit | Good fit
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
11
Notes: This is a practical tool students can literally apply to their own course project — read down the left column to find the row(s) that describe their project, then read across for the best-fit model.

## Slide 12
WORKED EXAMPLE
Worked Example — Choosing a Model for a Real Scenario
Scenario — a hospital needs a new patient-records system: requirements are largely fixed by regulation (HIPAA), the cost of a defect is high, and the system must pass a formal compliance audit before launch.
Step 1 — check the decision matrix rows: 'stable, fully understood requirements' → points to Waterfall; 'hard compliance / audit requirements' → points to Waterfall or Spiral.
Step 2 — check project scale and risk: this is a large, high-cost, high-risk system (patient safety, legal liability) → the matrix's 'large scope, high risk' row points to Spiral.
Step 3 — decision — Spiral is chosen: its explicit risk-analysis loops suit the compliance and safety risk, while still allowing incremental engineering rather than one long, all-or-nothing Waterfall pass.
Step 4 — contrast — a student team building a course-registration app (Week 2's earlier example) would read the matrix very differently: small scope, evolving requirements → Agile or RAD, not Spiral.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
12
Notes: The explicit contrast in Step 4 reinforces that there's no universally 'best' model — the same decision matrix produces a different, equally correct answer depending on the project's actual risk profile and scale.

## Slide 13
PRACTICAL CONTEXT · REAL INCIDENT
Case in Point — The FBI's $170M Virtual Case File
What happened — from 2000-2005, the FBI contracted a single vendor to build a new case-management system using a rigid, Waterfall-style approach with requirements largely fixed up front.
The problem — requirements kept changing as the project proceeded (a common reality for a novel, large system), but the Waterfall structure made each change extremely costly to absorb.
The outcome — after four years and over $170 million spent, the software was found 'incomplete, inadequate, and so poorly designed' that it was unusable, and the project was cancelled in April 2005.
The lesson — this matches the decision matrix directly: evolving requirements is the exact condition where Waterfall performs poorly, regardless of budget or vendor quality.
The aftermath — the FBI's replacement project (Sentinel) eventually succeeded by shifting toward smaller, incremental phases with closer user involvement — closer to the Agile end of the spectrum.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
13
Notes: This is a real, well-documented, publicly reported case (U.S. GAO reports and press coverage are public record). The teaching point connects directly back to the decision matrix: this project sat in exactly the row where Waterfall is the poor fit, and the outcome bore that out.

## Slide 14
5.1 PITFALLS
Common Pitfalls by Model
Model | Common Pitfall | Fix
Waterfall | Treating an early sign-off as unchangeable, even when it's clearly wrong | Build in a formal, lightweight change-request process
Agile | Sprints with no clear goal, becoming just 'two weeks of tasks' | Every sprint should have one clear, demoable objective
RAD | The prototype becomes production code without a security/scalability review | Treat cutover as a real hardening phase, not just a demo-to-launch flip
Spiral | Risk analysis becomes a rubber-stamp exercise instead of genuine analysis | Require a named, specific risk and mitigation for each loop, not a checklist
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
14
Notes: Each pitfall here is the model's core strength turned into a weakness through poor discipline — Waterfall's structure becomes rigidity; Agile's flexibility becomes aimlessness; RAD's speed becomes recklessness; Spiral's risk focus becomes bureaucracy.

## Slide 15
RECAP
By the End of Today You Can…
1
Diagram all four models — Sketch Waterfall, Agile, RAD, and Spiral from memory.
2
Compare them structurally — Use the comparison matrix to contrast planning style, risk handling, and best fit.
3
Read a burndown chart — Diagnose what a given ideal-vs-actual shape suggests about a sprint.
4
Apply a decision matrix — Choose the right model for a project based on its requirements stability and risk.
5
Learn from a real failure — Explain why Waterfall was a poor fit for the FBI's Virtual Case File.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
15
Notes: Quick self-check before Day 2: Agile Rituals & Spiral Risk, which goes deeper into two of today's models — the Spiral risk cycle in more detail, and Agile's specific ceremonies (standups, retros, sprint planning).

## Slide 16
SUMMARY
Key Takeaways
Waterfall is fully sequential and predictable, but expensive to reverse once a phase is signed off — best for stable, well-understood requirements.
Agile iterates in short sprints, adapting continuously — best for evolving requirements with active stakeholder engagement.
RAD prioritises fast, user-driven prototyping — best for small-to-mid scope apps where speed to a working prototype matters most.
Spiral adds an explicit risk-analysis step to each cyclical loop — best for large, high-risk, high-cost projects.
The FBI's Virtual Case File shows the real cost of mismatching model to project: $170 million spent using a rigid approach on a project with evolving requirements — exactly the condition the decision matrix flags as a poor fit.
CSE 0613-2209 · Web Programming | Week 5 · Development Methodologies
16
Notes: Summarise the five key points. Bridge to Day 2: Agile Rituals & Spiral Risk, which expands on two of today's four models in much greater depth.