## Slide 1
CSE 0613-2209 · Web Programming
Module 3: Methodology Deep Dive & Relationship Analysis
Week 5, Day 2 — Agile Rituals & Spiral Risk
A deeper look at the Spiral Model's risk cycles, the Cost-of-Change curve, and every Scrum role and ceremony explained.
Department of Computer Science and Engineering
Notes: Bridge from Day 1: we introduced Spiral and Agile at a survey level. Today we go deep on two things: the Spiral Model's expanding risk cycles, and the specific roles and rituals that make Agile/Scrum work day to day.

## Slide 2
WEEK 5 · DAY 2
This Session at a Glance
The Spiral Model's risk cycles, drawn as expanding loops
The Cost-of-Change curve — why late-discovered defects cost exponentially more
Every Scrum role and its responsibilities
Every Scrum ritual — purpose, frequency, and participants
A real two-week sprint, mapped day by day
Why This Matters
The Cost-of-Change curve is the mathematical justification for why Agile's short cycles and Spiral's risk analysis both exist — catching problems early isn't just tidier, it's dramatically cheaper.
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
2
Notes: Preview the five topics. This session directly deepens two of Day 1's four models, using the Cost-of-Change curve as the unifying justification for both.

## Slide 3
FIGURE 5.6
The Spiral Model's Expanding Risk Cycles
Each loop outward represents one full pass through Objectives → Risk Analysis → Engineering → Planning, at increasing scale and cost.
Start
Loop 1: Concept
Loop 2: Prototype
Loop 3: Production
1. Objectives
2. Risk Analysis
3. Engineering
4. Planning
Reading This Diagram
Each loop is a complete cycle through all four quadrants. The radius represents cumulative cost and commitment — Loop 1 might be a cheap paper prototype; Loop 3 might be the production-ready release.
Crucially, risk analysis (quadrant 2) happens every single loop — the project can be cancelled or redirected at the end of any loop if risk analysis reveals it's not worth continuing, before the next, more expensive loop begins.
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
3
Notes: Walk clockwise from Start through all four quadrants for Loop 1, emphasise the risk-analysis checkpoint, then show how Loop 2 repeats the same four quadrants at a larger radius (cost). This is the 'off-ramp' property that makes Spiral suited to high-risk projects: bad ideas get killed cheaply, in an early loop, before large sums are committed.

## Slide 4
WORKED EXAMPLE
Worked Example — A Spiral Loop in Practice
Scenario — a startup is building a novel AR shopping app; the biggest unknown is whether users will trust AR-based size recommendations enough to buy.
Loop 1 (cheap) — Objectives: validate user trust. Risk Analysis: the risk is 'nobody trusts it', mitigated by testing with 20 users on a paper-prototype video, not real code. Engineering: build a clickable mockup only. Planning: if trust is low, pivot before writing a line of production code.
Loop 2 (moderate cost) — Objectives: validate technical feasibility. Risk Analysis: the risk is 'AR sizing is inaccurate on real devices', mitigated by a working prototype tested on 5 phone models. Engineering: build a minimal real AR feature. Planning: proceed only if accuracy meets a defined threshold.
Loop 3 (full investment) — Objectives: full feature build. Risk Analysis: risk is now scaling and app-store approval, not user trust or feasibility — those were already retired in Loops 1 and 2. Engineering: full production build. Planning: launch.
Key insight — each loop retires the single biggest remaining risk before spending more, so the most expensive commitment (Loop 3) only happens once the riskiest unknowns are already resolved cheaply.
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
4
Notes: This example shows the spiral diagram from the previous slide applied concretely — each loop has a genuinely different, specific risk, and the cost only escalates after that risk is addressed, not before.

## Slide 5
FIGURE 5.7
The Cost-of-Change Curve
The relative cost of fixing a defect grows exponentially the later it's discovered in the process.
Chart: Relative cost to fix (×)
| Requirements | Design | Implementation | Testing | Production
Relative cost to fix | 1 | 3 | 8 | 25 | 100
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
5
Notes: These relative multipliers (1x/3x/8x/25x/100x) are the classic, widely-taught illustrative figures from Barry Boehm's software economics research — exact multiples vary by study, but the exponential shape is the consistently reproduced finding, and it's the whole justification for both Agile's short feedback loops and Spiral's early risk analysis.

## Slide 6
WORKED EXAMPLE
Worked Example — Same Bug, Different Discovery Point
Scenario — a missing null-check on a payment form field would take a developer about 20 minutes to fix if caught while writing the code.
Caught in Requirements review — cost ≈ 20 minutes × 1 = 20 minutes (just a documentation note).
Caught in Testing — cost ≈ 20 minutes × 25 = ~8.3 hours (root-causing a hard-to-reproduce bug, retesting, redeploying to the test environment).
Caught in Production — cost ≈ 20 minutes × 100 = ~33 hours (incident response, hotfix, emergency deploy, customer communication, and possible reputational cost).
Takeaway — this is precisely why Agile's short sprints (fast feedback) and Spiral's early risk analysis both exist: the goal in both models is to move the discovery point as far left on this curve as possible.
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
6
Notes: This arithmetic makes the exponential curve concrete and personal — the same tiny 20-minute fix becomes a 33-hour production incident purely because of when it was caught, not because the bug itself changed.

## Slide 7
5.2 SCRUM ROLES
The Three Scrum Roles
Role | Responsible For | Not Responsible For
Product Owner | Prioritising the backlog; deciding what gets built and in what order, representing business/user needs | How the team implements a story technically
Scrum Master | Facilitating rituals, removing blockers, protecting the team from scope disruption mid-sprint | Assigning tasks or dictating technical decisions
Development Team | Estimating, building, and testing the work; deciding how to implement each story | Deciding what to build or in what priority order
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
7
Notes: The 'Not Responsible For' column is deliberately included — the most common real-world Scrum dysfunction is a Product Owner dictating implementation details, or a Scrum Master acting as a traditional project manager assigning tasks.

## Slide 8
FIGURE 5.8
The Scrum Ritual Cycle
Four ceremonies structure every sprint, plus one daily ritual that repeats throughout.
Sprint Planning
Team commits to a scoped set of backlog items for the sprint
Daily Standup
15-min daily sync: progress, plans, blockers — repeats every day
Sprint Review
Demo completed work to stakeholders for feedback
Retrospective
Team reflects on process: what to keep, stop, start
Cycle repeats every sprint (1-4 weeks)
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
8
Notes: Point out that Daily Standup is the odd one out — it's the only ritual that repeats every single day rather than once per sprint, which is why it's highlighted differently. The Retrospective's output should visibly change the next sprint, or the ritual becomes pointless box-checking.

## Slide 9
5.2 RITUAL DETAILS
Every Ritual — Purpose, Timing, and Participants
Ritual | Frequency / Duration | Purpose | Participants
Sprint Planning | Once per sprint, ~2 hrs for a 2-week sprint | Select and commit to sprint scope | Whole team
Daily Standup | Every day, ~15 minutes | Sync on progress and surface blockers early | Development team (+ Scrum Master)
Sprint Review | Once per sprint, ~1 hr | Demo working software; gather stakeholder feedback | Whole team + stakeholders
Retrospective | Once per sprint, ~45 min | Improve how the team works, not what it builds | Whole team
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
9
Notes: This table is the practical reference students can literally use to run their own course project's Scrum process — durations scale down proportionally for shorter sprints.

## Slide 10
WORKED EXAMPLE
A Real Two-Week Sprint, Day by Day
Day | What Happens
Day 1 (Monday) | Sprint Planning in the morning; team begins work on top-priority stories in the afternoon
Days 2–4 | Daily Standup each morning; development and testing proceed on committed stories
Days 5 | Daily Standup; mid-sprint check — burndown reviewed (Day 1's chart) to catch drift early
Days 6–9 | Daily Standup continues; remaining stories completed, code reviewed, and merged
Day 10 (Friday) | Sprint Review (demo to stakeholders) in the morning; Retrospective in the afternoon; next Sprint Planning begins the following Monday
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
10
Notes: This maps every ritual from the previous two slides onto a literal calendar — use it as a template students can adapt directly for their own course-project sprints.

## Slide 11
PRACTICAL CONTEXT
Case in Point — A Retrospective That Actually Changed Something
Symptom — a student team's burndown chart showed the same pattern every sprint: flat for a week, then a rushed drop right before the Sprint Review.
Retrospective discussion — the team realised stories weren't being marked 'done' until fully polished, so real progress was invisible on the board until the very end.
Change agreed — split the Definition of Done into visible sub-states (In Progress → Code Review → Testing → Done) so the board reflects real progress daily, not just at the finish line.
Result — the next sprint's burndown tracked much closer to the ideal line, and the team caught a scope problem on Day 6 instead of Day 9, giving them time to descope rather than rush.
Lesson — this is exactly the Cost-of-Change principle applied to process itself: catching a process problem in the Retrospective (cheap) is far better than discovering it via a missed deadline (expensive).
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
11
Notes: This case study deliberately mirrors the burndown-pattern table from Day 1 ('flat line, then steep drop' pattern) and shows the Retrospective ritual as the mechanism that actually fixes it — tying today's content directly back to yesterday's.

## Slide 12
5.2 PITFALLS
Common Pitfalls in Agile Rituals & Spiral Risk
Pitfall | Why It's a Problem | Fix
Daily Standup becomes a status report to the Scrum Master | Kills the peer-to-peer coordination the ritual exists for | Redirect: team talks to each other, not to one person
Retrospective identifies problems but nothing changes | The ritual becomes a scheduled complaint session | Agree on one concrete, assigned action item per retro
Spiral risk analysis skipped 'because we're confident' | Confidence is not the same as an evaluated risk | Require a named risk and mitigation before each loop, always
Product Owner absent from Sprint Review | Team loses the feedback loop that justifies the whole process | Treat Sprint Review attendance as non-negotiable
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
12
Notes: Each pitfall here is a ritual or model element being performed in name only, without its actual purpose — the fixes all point back to re-connecting the ritual to why it exists in the first place.

## Slide 13
RECAP
By the End of Today You Can…
1
Diagram Spiral risk cycles — Explain what each expanding loop represents and why risk analysis repeats every loop.
2
Apply the Cost-of-Change curve — Estimate how much more expensive a defect becomes the later it's caught.
3
Name Agile roles — Distinguish Product Owner, Scrum Master, and Development Team responsibilities.
4
Explain Scrum rituals — State the purpose, timing, and participants of each of the four ceremonies.
5
Run a real sprint — Map all rituals onto a literal two-week calendar for a course project.
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
13
Notes: Quick self-check before Week 6, which shifts to Module 3's second focus: Relationship Analysis Principles — taxonomy classification and graph visualisation.

## Slide 14
SUMMARY
Key Takeaways
The Spiral Model's loops expand in cost and commitment, but risk analysis repeats every loop — bad ideas can be killed cheaply in an early loop before expensive commitment.
The Cost-of-Change curve is exponential: the same defect can cost roughly 100× more to fix in production than in requirements review — this is the shared justification for Agile's short cycles and Spiral's early risk analysis.
Scrum has three roles (Product Owner, Scrum Master, Development Team) with clearly separated responsibilities.
Scrum has four core rituals (Planning, Daily Standup, Review, Retrospective) plus the daily standup — each with a specific purpose that fails if performed in name only.
A real sprint maps every ritual onto a literal calendar — use the Day-by-Day template directly for your own course project.
CSE 0613-2209 · Web Programming | Week 5 · Agile Rituals & Spiral Risk
14
Notes: Summarise the five key points. Bridge to Week 6: Relationship Analysis Principles, which shifts from process methodology to modeling how content relates — taxonomy classification and graph visualisation.